## TODO 4
Status | Section | Task | Notes
needs styling | global | Order History navigation from left side bar to top menu
done | global | print/download icons in line with h1 Page Title
needs styling | global | left sidebar style change
| global | h1 page title change per page
| global | counts next to facets
| orders | combine order date and PO in same column
| orders | new grouping logic for multiple orders on same time stamp
| orders | new orders table styling
| orders | pull in backorders
done | invoice | no invoice specific changes
| shipments | add carrier above tracking number
| shipments | switch PO and invoice #
| manufacturers | remove pagination add lazy load
| gl codes | remove pagination add lazy load
| order detail | new template (search on top no left sidebar)
| order detail | new data: subtotal freight fees tax
| shipment detail | same template as order detail
| shipment detail | add track package button
| invoice detail | same template as order detail
| manufacturers detail | same template as order detail BUT date range filtering

## Sprint 4
Status | WRENCH | Section | Title | Notes
done | 245 | Invoices | Remove order # add invoice due date
done | 234 | Manufacturers | add date range labels | Done
done | 252 | Manufacturers | Counts and Graph
done | 253 | Manufacturers | manufacturer detail sort and pagination
done | 276 | Manufacturers | Additional Sort option | no styling
done | 277 | Manufacturers Detail | Bar graph item quantity | no change in styling
done | 293 | GL Codes | Bar charts
done | 300 | GL Codes | Detail Page Template
done | 294 | GL Codes | Spend rollup info next to bar chart
geekhive | 295 | GL Codes | Paging and sorting | no styling
needs search icon | 255 | Orders | Search on orders page
geekhive | 79 | Security | Change Account | no styling
geekhive | 297 | Tech Spike | Solar Search | no styling
half done | 256 | Orders | Filter by date range | Done
half done | 274 | Invoices | Download invoices | flyout menu - Done
waiting on design | 254 | Manufacturers | manufacturer detail template
waiting on design | 233 | Manufacturers | manufacturer detail page
waiting on design | 249 | Invoices | Invoice Detail Page
closed | 152 | Orders | Flter by controlled substance | md-checkbox
closed | 154 | Orders | Filter by address
closed | 138 | Orders | Filter by GL Codes
new side bar styling | 390 | Global | Global Template Changes
| 394 | Shipments | Add carrier switch PO and Invoice #
| 392 | Orders | Still need rollup before styling

## design discussion
radio buttons vs checkboxes
date range affecting top 5 manufacturers graph, but no other facets

## Sprint 3
WRENCH # | Title
WRENCH-81 | Order History - View Purchase History Bar Chart per manufacturer | done
WRENCH-178 | Order History - Shipments View - List orders by shipment | need design review and no tracking number styling
WRENCH-183 | Order History - create order detail template
WRENCH-179 | Order History - View Order Details | 1st pass done
WRENCH-184 | Order History - create invoice detail template
WRENCH-142 | Order History - invoice view - view invoice details | 1st pass done
WRENCH-150 | Order history pagination | styling done
WRENCH-143 | Order History - Invoice View - Header
WRENCH-185 | Order History - create GL code view template | waiting for template?
WRENCH-136 | Order histroy - GL code view - Top 5 graph and list

## TODO 3
Status | Category | Task | Notes
| dashboard | min height on dashboard modules
| global | mwi logo is jagged | 193 x 34 check explicit height width in svg code windows only?
done | global | blue active border around inputs | $cta-color 2px
geekhive working |  | paging active page doesn't change
done |  | order / invoice detail page change h1 and side bar
talk to geekhive |  | order / invoice detail page format address
done |  | bread crumbs
with design |  | manufacturers bar chart needs date title for filter and 13 month with new design
with design |  | shipments tracking number vs no tracking provided styling
geekhive |  | paging - what should it look like? first last current +/- one | < first ... -1 active +1 ... last >
done |  | main search 16px
|  | history icon cut off on bottom | *fine on windows vm
loading icon per module
in top nav lists plural not list
|  | border bottom on top nav doesn't line up | *fine on windoes vm
paging arrow icon
paging flush right
paging flush left
items per page baseline to number per page
done |  | blue side bar even padding top bottom for blue
done |  | Order history header line baseline with search bar in left side nav
in sub nav order history active state on top nav
with design |  | order history orders page -- changing
with design |  | order history invoices
osama working |  | add year to charting under january only
dropdown sort labels

## Looking Ahead
Looking ahead
Create empty dropdowns
Animations: what first?